## Sheet1
SEVERITY
| Risk | Statement | Response | Objective | Likelihood | Impact | Risk Level |  |  | Minimal | Minor | Moderate | Major | Severe
1 | Strain injuries | Working for too long may induce strain injury | Get up and move around every now and again | Maintain a reasonable level of comfort while working | Expected | Minimal | 4 | LIKELIHOOD | Guaranteed | 5 | 10 | 15 | 20 | 25
2 | Back injuries | sitting with bad posture for too long may induce injury | use correct posture and chairs with lumbar support | Prevent back injuries from long work periods | likely | minor | 6 |  | Expected | 4 | 8 | 12 | 16 | 20
3 | Worn out keyboards | typing too much will wear out keyboards faster | minimise typing by reducing coding waste | extend longevity of keyboards | possible | minimal | 2 |  | Likely | 3 | 6 | 9 | 12 | 15
4 | Deadline not being met | The trainee might struggle to hit the deadline | provide support and review deadline timing | ensure all work is completed on time | likely | Severe | 15 |  | Possible | 2 | 4 | 6 | 8 | 10
5 | data leaks | not following security practices increases risk of data leaks | ensure all security practices are followed at all times | maintain security of all data at all times | possible | Severe | 10 |  | Unlikely | 1 | 2 | 3 | 4 | 5
6 | Messy/unreadable code | not following coding standards can lead to unreadable code | ensure all coding practices are being followed by all engineers | maining easy to read, clean code | Expected | Moderate | 12
7 | Testing issues | Trainee might not be able to get good coverage during testing | Give more training with testing to enhance trainee knowledge | hit industry standard 80% coverage | Expected | Moderate | 12
8 | Not delivering a finished product | Trainee might not be able to reach a finished functional product | Give extra support in areas trainee was struggling to enhance learning | Understand Java enough to deliver a finished product | likely | Severe | 15
9 | Stress related issues | Project might induce stress related issues with trainee | Give direction to trainee to reduce stress and panic | Work with minimal stress to avoid mental health issues | Expected | Severe | 20
10 | Functionality issues | due to inexperience there may be functionality issues on the front end | attempt to ensure functionality is there when possible | Achieve MVP and deliver a working product | Expected | Major | 16
11 | GitHub issues | Trainee might have issues utilising git functionality | Give more time with Git to learn from experience | Uderstand and be able to fully untilise Git | Guaranteed | Minor | 10